QUALITY CONTROL PLAN

This QC Plan is designed mainly guide for the inspection and acceptance of all the deliverables that will be contracted for under the tender for evaluating GIRL-H Program in Kenya, Uganda, and Haiti

| PR/MAR # NBO 1087 | Tender #: MCK/NBO/10/2021 |
| --- | --- |
| PR/MAR Description: Evaluating GIRL-H Program in Kenya, Uganda, and Haiti |  |

The QC Plan details the procedures to inspect and determine the acceptability of the of the deliverables for this assignment.

# Essential Specifications and Testing Requirements Deliverable: Comprehensive Research Plan Parameter; Target Value; Margin of Error (Absolute or Relative); Testing Method; Performed / Reviewed by:. Inception Report; 1; Absolute; Document Review; QC Team. Key research questions; 1; absolute; Document Review; QC Team. Evaluation design; 1; Absolute; Document Review; QC Team. Sample Size Determination & Sampling Strategy; 1; absolute; Document Review; QC Team. Indicators; 1; absolute; Document Review; QC Team. Detailed data analysis plan including gender disaggregation; 1; absolute; Document Review; QC Team. Data Collection Plan; 1; absolute; Document Review; QC Team. Detail on frequency and seasonality of surveys; 1; absolute; Document Review; QC Team. Cost Analysis Approach; 1; absolute; Document Review; QC Team. Two workshops supporting Design of Approach; 1; absolute; Document Review; QC Team. Data Dissemination Plan; 1; Absolute; Document Review; QC Team. Deliverable: Data Collection Package Parameter; Target Value; Margin of Error (Absolute or Relative); Test; Performed / Reviewed by:. Quantitative Instrument; 1; absolute; Document Review; QC Team. Qualitative Instruments; 1; absolute; Document Review; QC Team. Enumerator training guidance; 1; absolute; Document Review; QC Team. Data collection protocols; 1; absolute; Document Review; QC Team. Quality Control Protocol; 1; absolute; Document Review; QC Team. Reporting Templates; 1; absolute; Document Review; QC Team. Deliverable: Training Team on Protocols Parameter; Target Value; Margin of Error (Absolute or Relative); Testing Method; Performed / Reviewed by:. 3-day Training; 1; + or – 1 day; Participation/Visual; QC Team. Training Report; 1; Absolute; Document Review; QC Team. Deliverable: First round data analysis and brief Parameter; Target Value; Margin of Error (Absolute or Relative); Testing Method (Lab, Visual, Certificate…); Performed / Reviewed by:. Data Analysis Dashboard in Excel (it should include charts and tables); 1; Absolute; Visual Review; QC Team. Data analysis description; 1; Absolute; Document Review; QC Team. First Draft of Report; 1; Absolute; Document Review; QC Team. Deliverable: Second round data analysis and brief Parameter; Target Value; Margin of Error (Absolute or Relative); Testing Method (Lab, Visual, Certificate…); Performed / Reviewed by:. Data Analysis Dashboard in Excel (it should include charts and tables); 1; Absolute; Visual Review; QC Team. Data analysis description; 1; Absolute; Document Review; QC Team. Second Draft of Report; 1; Absolute; Document Review; QC Team. Executive Summary; 1; Absolute; Document Review; QC Team. Deliverable: Final data analysis, comprehensive report and combined brief Parameter; Target Value; Margin of Error (Absolute or Relative); Testing Method (Lab, Visual, Certificate…); Performed / Reviewed by:. Data Analysis Dashboard in Excel (it should include charts and tables); 1; Absolute; Visual Review; QC Team. Data analysis description; 1; Absolute; Document Review; QC Team. Final Report; 1; Absolute; Document Review; QC Team. Executive Summary; 1; Absolute; Document Review; QC Team.

# Contract Testing Requirements The GIRL-H team will appoint a quality control team, that includes the Director of Research and Evidence for GIRL-H, Country M&E Managers for Kenya, Uganda, and Haiti, GIRL-H Program Director (optional), member from HQ Research and Learning Team, and Regional MEL Advisor. This group will be responsible for discussing expectations on each deliverable with the firm/consultant, and jointly reviewing each deliverable, providing feedback and providing the final approval that the deliverable has met required standards following completion.

# Non-Conformance The quality control committee, as described above, will provide collective feedback on a product. If the product does not meet required standards, the quality control committee will provide two rounds of feedback on any product that does not meet the required standards. On the third round of feedback, the quality control committee will inform the service provider that their deliverable does not meet the required standards, and that they are at risk of losing payment for those deliverables. If the issues are still not corrected, the QC committee will meet with the GIRL-H Program Director, Director Operations, and HQ representative to determine which portion of payment will be withheld, and make a recommendation. The Program Director will be responsible for communicating to the firm/consultant about modified payments due to incompletion/poor completion of deliverables.

A relative margin of error will be indicated as a percent (example: +-5%); an absolute margin of error will be indicated as a value (example: +- 5cm)